## Sheet1
Jeremy Nelson
Bazinga!
Individual work schedule
CTC Office GUI
Task | Start | Days | Complete
Coding Standard | 2012-01-20 | 7 | 2012-01-27
Source Control/Defect Tracking set up | 2012-01-13 | 14 | 2012-01-27
Project and logging set up | 2012-01-27 | 7 | 2012-02-03
System SRS support and review | 2012-01-20 | 20 | 2012-02-09
CTC GUI SRS | 2012-02-03 | 6 | 2012-02-09
CTC GUI initial sketching | 2012-01-27 | 13 | 2012-02-09
CTC GUI architecture and design document | 2012-02-10 | 21 | 2012-03-02
UI Controls development and screen layout | 2012-02-10 | 21 | 2012-03-02
System Interfaces and data types implementation | 2012-02-17 | 7 | 2012-02-24
System architecture and design document support | 2012-03-08 | 14 | 2012-03-22
GUI Implementation and Integration | 2012-03-12 | 24 | 2012-04-05
System test plan support | 2012-03-15 | 7 | 2012-03-22
CTC GUI Test Plan | 2012-03-22 | 7 | 2012-03-29
Unit test implementation | 2012-03-22 | 7 | 2012-03-29
System integration and debugging | 2012-04-05 | 21 | 2012-04-26
Formalized system and component testing | 2012-04-12 | 7 | 2012-04-19
CTC GUI Help files | 2012-04-12 | 14 | 2012-04-26
CTC GUI Configuration Management Plan | 2012-04-19 | 7 | 2012-04-26
CTC GUI Installation Guide | 2012-04-19 | 7 | 2012-04-26
Formulas:
Complete = [Start]+[Days]